## Project Overview
RAJGIR MARATHON - STANDALONE WEBSITE & EVENT SYSTEM SPECIFICATION
Official Technical Feature Backlog & System Scope ¦ Based on Official Brochure Analysis
Project Attribute | Executive Description & Business Scope
Project Name | Rajgir Marathon Official Website & Event Management Ecosystem
Event Mottos & Slogans | • 'Run Through History' • 'One Run. Many Stories. Infinite Memories.' • 'Run with Purpose. Finish with Pride.'
Event Date & Venue | Winter 2026 ¦ Rajgir, Bihar, India
Organizing Body | Rajgir Marathon Executive Committee & Heritage Endurance
Official Contact Desk | Email: hello@rajgirmarathon.com ¦ Phone: +91 8882520326 ¦ Web: www.rajgirmarathon.com ¦ Location: Rajgir, Bihar, India
Target Audience | Runners (Full, Half, 10K, 5K, 3K), Volunteers, Corporate Sponsors, F&B/Expo Vendors, Heritage Tourists, Spectators, Media
Core Platform Scope | Dedicated digital marathon ecosystem delivering an end-to-end web portal, runner dashboard, RFID timing integration, live GPS course map, volunteer management system, sponsor marketplace, tourism guide, and admin operations panel.
Key System Deliverables | • High-Impact Public Website & Media Portal • Pre-Registration & Multi-Tier Online Registration System • RFID Chip Timing Ingestion & Real-Time Live Results Engine • Interactive GPS Course Route & Aid Station Map • Runner Dashboard (Digital Bib, Split Times, Verified PDF Certificates) • Volunteer Management Portal ('Team Rajgir') • Sponsor Inventory & Branding Marketplace • Rajgir Heritage Tourism & Accommodation Directory • Event Admin Control Center
Visual Theme & Aesthetics | Rich Dark/Gold/Red visual identity celebrating Rajgir's ancient history (Vishwa Shanti Stupa, Heritage Ruins) blended with high-energy modern marathon sports imagery.

## Portals & User Roles
RAJGIR MARATHON - PORTALS & USER ROLES MATRIX
Ecosystem Portals and Specialized Access Roles for Rajgir Marathon
Portal ID | Portal / Section Name | Target User Role | Key Functional Capabilities & System Scope | Access Level
PORT-01 | Public Visitor Portal | Public Visitors, Spectators, Tourists | Explore Rajgir heritage, view race categories, check event schedule, access tourist guide, view photo gallery, search FAQs, subscribe to newsletter. | Public Access (No Login)
PORT-02 | Runner Portal & Dashboard | Registered Runners (42K, 21K, 10K, 5K, 3K) | Pre-register & register for races, pay online, view Digital Bib, check RFID timing splits, download verified PDF certificates, access personal AI photo gallery. | Runner Account (OTP / Password)
PORT-03 | Volunteer Portal ('Team Rajgir') | Event Day Volunteers, Route Marshals | Apply for volunteer tracks, select preferred shift roles, view reporting schedule, check-in via QR pass, download official volunteer e-certificates. | Volunteer Account (Approval Needed)
PORT-04 | Sponsor & Brand Portal | Corporate Sponsors, Brand Partners | Browse branding inventory (Start/Finish Arch, Bib logo, Medals, LED screens), select package tier, upload vector artwork, download GST invoices. | Sponsor Account + GST Verification
PORT-05 | Vendor Operations Portal | F&B Vendors, Medical Teams, Expo Operators | Digital onboarding, stall location assignment, venue check-in pass generation, logistics coordination. | Vendor Entity Verification
PORT-06 | Media & Press Portal | Journalists, Photographers, Press Reporters | Apply for press accreditation, access high-res media kits, download official event photos, stream live press briefings. | Media Credential Audit & Approval
PORT-07 | Race Operations Admin Panel | Race Directors, Operations Team, Referees | Complete admin oversight: participant roster management, RFID timing split ingestion, volunteer roster approval, sponsor contract management, mass SMS/Email broadcasts. | Admin Multi-Factor Authentication

## Master Features Backlog
RAJGIR MARATHON WEBSITE - MASTER FEATURE BACKLOG
Complete Feature Specification for Rajgir Marathon Standalone Web & Event System
Feature ID | Module / Page / Section | Feature Name | Detailed Functional Requirements & Visual Specs | Platform Layer | Status | Priority | Target User Profile
RAG-FEAT-001 | Header & Navigation | Brand Logo & Slogan Header | Official Rajgir Marathon logo featuring runner graphic, Stupa emblem, and slogan 'Run Through History'. | Web Portal | Planned | High | All Visitors
RAG-FEAT-002 | Header & Navigation | Top Navigation Menu Links | 7 Main Navigation links: Home, About, Race Info, Events, Sponsors, Gallery, Contact. | Web Portal | Planned | High | All Visitors
RAG-FEAT-003 | Header & Navigation | Social Media Header Icons | Quick-link icons for Instagram, Facebook, X (Twitter), and YouTube. | Web Portal | Planned | Medium | All Visitors
RAG-FEAT-004 | Header & Navigation | Sticky Header Bar | Blur backdrop sticky header on scrolling for seamless site navigation. | Web Portal | Planned | Medium | All Visitors
RAG-FEAT-005 | Hero Banner | Main Title & Visual Backdrop | Hero section overlaying runners onto Vishwa Shanti Stupa background with 'RAJGIR MARATHON' & 'COMING SOON'. | Web Portal | Planned | High | All Visitors
RAG-FEAT-006 | Hero Banner | Event Date & Location Badge | Prominently displays 'RAJGIR, BIHAR ¦ WINTER 2026' with location pin icon. | Web Portal | Planned | High | All Visitors
RAG-FEAT-007 | Hero Banner | Event Slogan Quote Card | Badge displaying slogan: 'One Run. Many Stories. Infinite Memories.' | Web Portal | Planned | Medium | All Visitors
RAG-FEAT-008 | Hero Banner | Interactive Race Countdown Clock | Live animated countdown timer counting down days, hours, and minutes to Winter 2026 event kick-off. | Web Portal | Planned | High | All Visitors
RAG-FEAT-009 | Primary Action Hub | Register As Runner Card Button | Red primary card button with runner icon driving runner pre-registrations. | Web Portal | Planned | High | Runners
RAG-FEAT-010 | Primary Action Hub | Register As Volunteer Card Button | Gold card button with team icon driving volunteer applications. | Web Portal | Planned | High | Volunteers
RAG-FEAT-011 | Primary Action Hub | Become A Sponsor Card Button | Dark card button with handshake icon driving corporate sponsorship inquiries. | Web Portal | Planned | High | Sponsors & Brands
RAG-FEAT-012 | Primary Action Hub | Heritage & Spirituality Experience Card | Showcase card displaying 'Experience the perfect blend of Heritage, Nature & Spirituality'. | Web Portal | Planned | Medium | Tourists & Spectators
RAG-FEAT-013 | Feature Highlights Bar | Ancient Heritage Route Badge | Icon badge highlighting the historical marathon trail past Rajgir stupas and ancient ruins. | Web Portal | Planned | High | All Visitors
RAG-FEAT-014 | Feature Highlights Bar | Professional Race Management Badge | Icon badge detailing certified race directors and world-class management. | Web Portal | Planned | High | Runners
RAG-FEAT-015 | Feature Highlights Bar | RFID Timing Badge | Icon badge highlighting electronic chip timing for accurate split records. | Web Portal | Planned | High | Runners
RAG-FEAT-016 | Feature Highlights Bar | Medical Support Badge | Icon badge detailing emergency medical posts, ambulances, and doctor support. | Web Portal | Planned | High | Runners & Families
RAG-FEAT-017 | Feature Highlights Bar | Hydration Stations Badge | Icon badge detailing water, electrolyte, and aid stations along the course. | Web Portal | Planned | High | Runners
RAG-FEAT-018 | Become A Runner | Race Distance Selector Pills | Interactive selector for 5 distances: 42.2 KM (Full), 21.1 KM (Half), 10 KM, 5 KM, and 3 KM (Fun Run). | Web Portal | Planned | High | Runners
RAG-FEAT-019 | Become A Runner | Runner Amenities & Kit Grid | Display grid showing included perks: Finisher Medal, Premium T-Shirt, Digital Certificate, Live Tracking, Professional Timing, Entertainment & More. | Web Portal | Planned | High | Runners
RAG-FEAT-020 | Become A Runner | Pre-Register Now Modal Form | Pop-up modal capturing runner pre-registration details (Name, Email, Mobile, Age, Distance interest). | Web Portal | Planned | High | Runners
RAG-FEAT-021 | Registration Engine | Multi-Step Registration Wizard | Guided registration wizard collecting personal data, medical clearance, emergency contact, T-shirt size, and legal waiver. | Web Portal | Planned | High | Runners
RAG-FEAT-022 | Registration Engine | Online Payment Gateway Integration | Instant online payment checkout supporting UPI (GPay/PhonePe), Credit/Debit Cards, NetBanking, and Wallets. | Web Portal | Planned | High | Runners
RAG-FEAT-023 | Registration Engine | Automated GST Tax Invoice PDF | Instant downloadable GST-compliant tax invoice PDF generated post-payment. | Web Portal | Planned | High | Runners
RAG-FEAT-024 | Registration Engine | Digital Bib & Security QR Generator | Automated allocation of sequential bib numbers and dynamic check-in QR code for pre-race Expo pickup. | Web Portal | Planned | High | Runners
RAG-FEAT-025 | Live Results Engine | RFID Split Timing Ingestion System | Connects with electronic RFID mat hardware to capture real-time split times at Start, 5K, 10K, 21K, and Finish. | Web & System | Planned | High | System
RAG-FEAT-026 | Live Results Engine | Real-Time Race Timing Search | Spectator search engine allowing instant result lookup by Bib Number, Runner Name, or Distance Category. | Web Portal | Planned | High | All Visitors
RAG-FEAT-027 | Live Results Engine | Master Leaderboards & Ranks | Tabbed leaderboards for Overall Winners, Gender Rankings, Age Categories, and Corporate Challenge. | Web Portal | Planned | High | All Visitors
RAG-FEAT-028 | Live Results Engine | Verified PDF Certificate Downloader | One-click download of official high-resolution PDF certificate with verified chip timing split badges. | Web Portal | Planned | High | Runners
RAG-FEAT-029 | Live Results Engine | Social Media Result Card Generator | Generates branded graphic image summarizing runner finish time, rank, and pace for instant social media sharing. | Web Portal | Planned | High | Runners
RAG-FEAT-030 | Interactive Route Map | Interactive Course GPS Map | Interactive map displaying certified 42.2K, 21.1K, 10K, 5K, and 3K route lines over Rajgir terrain. | Web Portal | Planned | High | Public & Runners
RAG-FEAT-031 | Interactive Route Map | Dynamic Terrain Elevation Profile | Interactive graph showing elevation gains, hill challenges, and altitude profile along the course. | Web Portal | Planned | High | Runners
RAG-FEAT-032 | Interactive Route Map | Filterable Race-Day Station Markers | Filterable map overlays for Hydration/Water Stations, Medical Tents, Washrooms, Parking, Photography Points, and Entertainment. | Web Portal | Planned | High | Public & Runners
RAG-FEAT-033 | Runner Dashboard | Personal Profile & Race Records | Dashboard allowing runners to view profile details, bib number, upcoming race countdown, and past split times. | Web Portal | Planned | High | Runners
RAG-FEAT-034 | Runner Dashboard | Personal AI Photo & Video Gallery | AI bib-matched photo gallery allowing runners to view photos, purchase high-res copies, and watch finisher videos. | Web Portal | Planned | High | Runners
RAG-FEAT-035 | Join Team Rajgir | Volunteer Header & Hero Section | Section titled 'JOIN TEAM RAJGIR - BE THE HEART OF THE MARATHON' with volunteer artwork. | Web Portal | Planned | High | Volunteers
RAG-FEAT-036 | Join Team Rajgir | 10 Volunteer Tracks Showcase | Grid displaying 10 volunteer tracks: Route Marshal, Registration Desk, Hydration Station, Medical Support, VIP Management, Expo & Village, Media Team, Photography, Social Media, Finish Line Operations. | Web Portal | Planned | High | Volunteers
RAG-FEAT-037 | Join Team Rajgir | Become A Volunteer Application Modal | Form capturing applicant contact details, track interest, availability, T-shirt size, and past experience. | Web Portal | Planned | High | Volunteers
RAG-FEAT-038 | Join Team Rajgir | Volunteer Shift Schedule & QR Check-In | Dashboard for volunteers to view shift schedules, venue reporting location, and check in via QR code pass. | Web Portal | Planned | High | Volunteers
RAG-FEAT-039 | Join Team Rajgir | Volunteer Digital Certificate Download | Post-event download page for official Volunteer Service Certificate signed by Race Directors. | Web Portal | Planned | High | Volunteers
RAG-FEAT-040 | Why Participate | 8 Feature Highlight Cards | Grid of 8 cards: 1. Scenic Route, 2. World Class Event, 3. Finisher Medal, 4. Premium T-Shirt, 5. RFID Timing, 6. Medical Support, 7. Family Experience, 8. Local Tourism Experience. | Web Portal | Planned | High | All Visitors
RAG-FEAT-041 | Rajgir Tourism Guide | Heritage & Eco-Tourism Showcase | Detailed guide to Vishwa Shanti Stupa, Glass Floor Skywalk, Nature & Zoo Safari, Hot Springs (Brahma Kund), and Ropeway. | Web Portal | Planned | High | Visitors & Runners
RAG-FEAT-042 | Rajgir Tourism Guide | Hotels & Accommodation Directory | Directory of hotels, resorts, and homestays in Rajgir with runner discount codes and direct booking links. | Web Portal | Planned | High | Visitors & Runners
RAG-FEAT-043 | Sponsor Portal | Corporate Sponsor Onboarding | Registration portal for brand partners, GST details upload, and sponsorship tier selection. | Web Portal | Planned | High | Sponsors
RAG-FEAT-044 | Sponsor Portal | Branding Inventory Marketplace | Select branding assets: Start Arch, Finish Arch, Bib logo, Medal ribbon, T-shirt logo, Water Stations, LED screens, etc. | Web Portal | Planned | High | Sponsors
RAG-FEAT-045 | Vendor Portal | Vendor Onboarding & Venue Pass Manager | Digital onboarding for F&B, Apparel, Medical, Logistics, and Expo booth operators with venue pass generation. | Web Portal | Planned | High | Vendors
RAG-FEAT-046 | Media Centre | Press Release Library & Accreditation | Downloadable press kit, press release library, and media press accreditation registration form. | Web Portal | Planned | Medium | Media
RAG-FEAT-047 | Media Centre | Live Video Streaming Player | Embedded video player streaming pre-race expo events, press meets, and live finish line coverage. | Web Portal | Planned | High | Media & Public
RAG-FEAT-048 | Admin Control | Race Operations Control Panel | Admin panel to manage participant rosters, RFID results upload, volunteer shift approvals, and mass SMS/Email broadcasts. | Web Admin | Planned | High | Super Admins
RAG-FEAT-049 | Stay Connected | Newsletter Email Lead Form | Input field 'Enter your email address' + 'SUBSCRIBE' button with instant validation & lead storage. | Web Portal | Planned | High | All Visitors
RAG-FEAT-050 | Stay Connected | Social Media Follow Hub | Icons linking to Instagram, Facebook, X (Twitter), YouTube, and LinkedIn accounts. | Web Portal | Planned | Medium | All Visitors
RAG-FEAT-051 | Organized By & Footer | Organizers Partnership Logo Block | Branding block: 'ORGANISED BY: MettleMiles X HERITAGE ENDURANCE'. | Web Portal | Planned | High | All Visitors
RAG-FEAT-052 | Organized By & Footer | Official Contact Details Block | Clickable contact desk: hello@rajgirmarathon.com, www.rajgirmarathon.com, +91 8882520326, Rajgir, Bihar, India. | Web Portal | Planned | High | All Visitors
RAG-FEAT-053 | Organized By & Footer | Calligraphy Artwork & Footer Bar | 'Run Through History' calligraphy artwork + Footer bar: 'RAJGIR MARATHON ¦ COMING SOON ¦ RUN WITH PURPOSE. FINISH WITH PRIDE.' | Web Portal | Planned | Medium | All Visitors

## Race Categories Matrix
RAJGIR MARATHON - RACE CATEGORIES MATRIX
Detailed Breakdown of the 5 Official Race Distance Categories
Category Code | Category Name | Distance | Target Runner Profile | Included Amenities & Kit | RFID Chip Timing | Medal & Certificate | Pre-Reg Status
RACE-42K | Full Marathon | 42.2 KM | Seasoned Distance Runners & Marathoners | Premium T-Shirt, Finisher Medal, Digital Cert, Live Tracking, Professional Timing, Aid Stations, Refreshments | Included | Included | Pre-Registration Open
RACE-21K | Half Marathon | 21.1 KM | Amateur & Intermediate Distance Runners | Premium T-Shirt, Finisher Medal, Digital Cert, Live Tracking, Professional Timing, Aid Stations, Refreshments | Included | Included | Pre-Registration Open
RACE-10K | 10K Run | 10.0 KM | Fitness Enthusiasts & Corporate Runners | Premium T-Shirt, Finisher Medal, Digital Cert, Live Tracking, Professional Timing, Aid Stations, Refreshments | Included | Included | Pre-Registration Open
RACE-05K | 5K Run | 5.0 KM | Beginners, Youth & Families | Event T-Shirt, Finisher Medal, Digital Cert, Refreshments, Medical Support | Optional | Included | Pre-Registration Open
RACE-03K | 3K Fun Run | 3.0 KM | Kids, Families, Senior Citizens & Beginners | Event T-Shirt, Finisher Medal, Digital Cert, Refreshments | Not Applicable | Included | Pre-Registration Open

## Volunteer Tracks
RAJGIR MARATHON - VOLUNTEER TRACKS MATRIX
Detailed Responsibilities and Perks across 10 Team Rajgir Tracks
Track Code | Volunteer Track Name | Brochure Icon | Key Responsibilities & Scope | Perks & Benefits
VOL-RM | Route Marshal | Flag / Route Icon | Manage route direction, runner safety, traffic control, and hydration points guidance along ancient heritage trail. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-RD | Registration Desk | Desk / User Icon | Manage runner bib distribution, kit check-in, registration verification, and query resolution. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-HS | Hydration Station | Water Drop Icon | Distribute water, electrolyte drinks, fruits, and energy gels to runners at aid stations. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-MS | Medical Support | Red Cross Icon | Assist medical team, first aid posts, rapid response ambulances, and runner support along route. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-VIP | VIP Management | Crown / Star Icon | Manage VIP lounge, chief guests, dignitaries, prize distribution area, and stage hospitality. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-EV | Expo & Village | Tent / Village Icon | Manage pre-race expo setup, sponsor stalls, photo booths, and runner bag drop stations. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-MT | Media Team | Megaphone / Mic Icon | Assist press reporters, media kit distribution, media lounge setup, and interviews coordination. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-PH | Photography | Camera Icon | Capture high-resolution photos of runners, heritage landmarks, finish line moments, and crowd. | Volunteer T-Shirt, RFID Badge, Certificate, Special Media Pass
VOL-SM | Social Media | Share / Mobile Icon | Live tweet, Instagram reels creation, story updates, and real-time social engagement during event. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments
VOL-FL | Finish Line Operations | Checkered Flag Icon | Distribute finisher medals, water bottles, foil blankets, and guide runners to recovery zone. | Volunteer T-Shirt, RFID Badge, Certificate, Refreshments